## Sheet1
Yes We Code! Capstone Logbook
Week | Worked on | Next Weeks Tasks | Scholar Weekly Update Submission
1 | Research and Practice Android Coding | Start on Mockups and Diagrams | With my project proposal approved, I’ve started to do some research and gather resources where needed. I talked to Prof. Perkins who is the professor of the Mobile Application Programming class to see if I could borrow a tablet for the semester and if he would be willing to answer any questions that I had. He said yes, but I need to go pick up the tablet from him either this week or next week. I started looking into making Java animations in Android Studio, but have only done about 1.5 hours, since I spent another hour downloading any updates to Android Studio and fixing settings. As for the module writing, I began researching information from other sources such as Codecademy and Udacity, since I already have accounts with them. I was thinking about asking one of the CPSC 150 or 250 professors to have access to their powerpoints. For the rest of the week I plan on continuing my research and creating an outline for my module.
2 | Mockups and Diagrams, research more on module lessons | More diagram and module critiques. Start researching for icons and images for visuals | Since the last update I have created my Github repository and capstone log using Google's version of Excel. This only took about an hour. I have also started on my phone/tablet mockups using Basalmiq, specifically the title/main screen, module section selection screen, and the module learning screen. The module learning screen will be classroom based: one section presents a chalkboard, a character in the corner presents a teacher, and a bottom section will be a text screen with the monologue. Designing and creating these mockups took about 3 hours. The only change to my plans is that I might switch from using Eclipse IDE to IntelliJ by JetBrains for Java. The rest of the week I start working on my class diagrams and continue making mockups.
3 | Finish mockup and diagram critiques. Place images in an organized file. Prepare presenation of intermediate milestone | Begin coding in Android Studio | I have continued working on my phone and tablet mockups, this time focusing on the game screens basic setup. I only got to spend about 2 hours on it, and will work on it more this week. I have also found a few sources needed for icons. As for my animations, I'm debating if I could create a few of them with a GIF maker or make GIFS from scratch. I'm still plan on making animations through Java, but I'm not sure how many of them I will have to do just yet, and therefore want alternate solutions if necessary. Other than that, there are no changes to my plan schedule.
4 | Begin Coding in Android Studio (Visuals and UI Design). Start on basic game code mechanics. | Continue working on gaming mechanics and animations. | This week my focus is on cleaning up my mockups, diagrams, and documentation in preparation for the intermediate milestone. By creating an presentation, I'm able to clearly see gaps in any work or information I've been missing. For example, I hadn't created any folders for organization on github, making it harder to find the items I needed. The my end goal this week is to reorganize myself and my work so that I can officially begin coding for my application in Android Studio.
5 | Lesson and Code Design | Heavy Coding into Android Studio | I focused a bit more on the design of my code this past weekend. I found mp3 files of notes that I can use for my music game, but I'm worried about copyright documentation, so I may just create my own mp3 files by recording myself on the clarinet or piano. I've also started storyboarding so I know when to present animations during a lesson, how long they'll stay on screen, and how often they will move. I have however created a few bare classes in android studio and got the application running. This weekend I hope to shift my focus into mainly coding. At this moment there are no major changes.
6 | LargeText Integration and Quiz Code; Intermediate Milestone Preparation | Continue Android Studio code integration | I've been working on the code for the application outside of Android Studio using mainly Java IntelliJ. My main focus was adding an File I/O method or class to read a text file for the lessons. The quiz game section of code is going well, and I don't see too many obstacles adding it to the application. For the rest of the week, I will work on the Intermediate Milestone which I think will best be presented using the android emulator and other software on my computer, but I am going to try and download an APK file onto a device. Also I'm connecting the music files for the music game application buttons using XML. Still no major changes to project.
7 | Android Studio Code Integration | Update Class Diagram; Adjusting Animations; Continue Android Studio Integration | This weekend I worked on using my Java code as guide to creating the classes needed in Android Studio. While working I reorganized my classes, which means I will have to update my class diagram. There were a few obstacles, but I was still able to implement the very basics on the application which still gives me plenty of time to finish my Capstone if I reduce the amount of time I dedicated to testing. I will present my Intermediate Milestone this week and continue fixing my code.
8 | Music Game code | Music game code; Proofreading and Editing lesson and quiz code. | Last week I've been adding the lesson plans and quiz questions into the application, and testing if the animations match up for when the information is presented. For the rest of the week and probably the week after I will be fixing the music game elements so that the music matches the commands.
9 | Music Game code; Testing on virtual and real devices. | Code Cleaning; Preparation for Capstone Submission | I made a good amount of progress on the lesson plans and animations. I'm dealing with a few issues with the music game, but my backup plan is to just make the game a little bit simpler. I've also began download testing on my old android phone and tablet. For the rest of the time left, I want to do a lot of code cleaning and resizing of images.